## Slide 1: Project JSON Data – JAN 2026
Dev Effort: S-Small, M-Medium, L-Large & XL- Extra Large
Action over
Action in Progress
Progress not as per plan
Action yet to start
Sl no. | Brief about change | What is the impact | Dev effort | Remarks | Gone Live/ETA | Status
1 | Login page UI revamp | Improved usability and accessibility | S | Deployed successfully | 10/10/2025 | 
2 | OTP retry logic added | Reduces login failures | M | Live in production | 12/10/2025 | 
3 | Password policy update | Stronger security compliance | M | Pending rollout | 18/10/2025 | 
4 | Dashboard API optimization | Faster load times | L | Performance testing ongoing | 20/10/2025 | 
5 | Role-based access control | Restricts unauthorized access | L | Blocked due to dependency | 25/10/2025 | 

## Slide 2: Project JSON Data – JAN 2026
Dev Effort: S-Small, M-Medium, L-Large & XL- Extra Large
Action over
Action in Progress
Progress not as per plan
Action yet to start
Sl no. | Brief about change | What is the impact | Dev effort | Remarks | Gone Live/ETA | Status
6 | Audit log enhancements | Better traceability | M | Development started | 28/10/2025 | 
7 | Session timeout handling | Improves security posture | S | Code review pending | 30/10/2025 | 
8 | Error message standardization | Clearer user feedback | S | Ready for deployment | 01/11/2025 | 
9 | Bulk upload validation | Prevents incorrect data entry | M | QA in progress | 05/11/2025 | 
10 | Email notification retry | Ensures delivery reliability | M | Delayed due to infra issue | 08/11/2025 | 

## Slide 3: Project JSON Data – JAN 2026
Dev Effort: S-Small, M-Medium, L-Large & XL- Extra Large
Action over
Action in Progress
Progress not as per plan
Action yet to start
Sl no. | Brief about change | What is the impact | Dev effort | Remarks | Gone Live/ETA | Status
11 | Admin report export | Easier operational reporting | L | Not yet started | 15/11/2025 |